Crew Deployment Gantt

Manager Quick Reference  ·  Tyler Rogers / Dale Forrest

# What This Tool Does

The Crew Deployment Gantt shows where every crew is scheduled across all active Paragon jobs for the next 19 weeks. When supers submit their weekly headcount from the field, the Gantt overlays their actual numbers against the master schedule baseline so you can see at a glance who matched plan, who is under-manned, and who called an audible.

# How to Access

paragontulsaresults.com/crew-schedule.html

Bookmark this URL. Works in any browser on desktop, tablet, or phone.

# Loading Live Crew Data

Supers submit their numbers from the field each Monday morning. To view their submissions:

| Step | Action |
| --- | --- |
| 1 | Go to crew-schedule.html |
| 2 | Set the WEEK date picker (top right) to the Monday of the week you want to review |
| 3 | Click the green "📡 Load Live Data" button |
| 4 | The green bar confirms: "Live: [Name(s)] — X row(s) for week of [date]" |

# Reading the Display

## Color Codes

| Color | Crew Type | Jobs |
| --- | --- | --- |
| Blue | Site Crew | 565, 574, 575, 577, 571, Rejoice, Riverline |
| Teal | Utility Crew | 566, 574 KSL, 565 Storm |
| Amber | Concrete Crew | 565 Elm, 571 BA, Muskogee Punch List |
| Green | Asphalt Crew | 571 BA, Berryhill, Averitt, Rejoice, 565 |
| Purple | NEI | 20117 Walmart, 2147 Rudisill, 2151 ORU |
| Dark Red | United Golf | 20229 Caswell, 20242 Hardscrabble CC |

## Live Data Indicators

When live data is loaded, cells with actual submissions show two chips stacked:

| Indicator | Meaning |
| --- | --- |
| Faded chip | Baseline from master schedule (what was planned) |
| ▼ Red # | Actual is LOWER than scheduled. Under-manned. Flag for review. |
| ▲ Green # | Actual is HIGHER than scheduled. Over-manned or scope added. |
| ● # same | Actual matches plan exactly. |
| No change | Super has not yet submitted for this week. Baseline only showing. |

## Filter Buttons

Click any crew type button in the toolbar to isolate that crew across all projects. Click "All Groups" to return to the full view. Useful for Tyler when reviewing utility crew deployment across multiple active jobs simultaneously.

# Who Submits What

| Name | Crew Type | Job(s) |
| --- | --- | --- |
| Jared | Site + Asphalt | 565 Jenks-Elm Street |
| Rolondo | Site | 571 BA - Jasper/Aspen |
| Elijah | Site | 575 SGL Airport |
| John | Site + Utility | 574 COT 91st Street |
| Jimmy | Site | 577 Kirby-Smith Yard |
| Randy | Concrete | 565 Elm St, 571 BA, Muskogee Punch List |
| Sergio | Utility | 566 COT Woodward Park |
| Anthony | Utility | 565 Jenks-Elm Street (Storm) |
| Rye | Asphalt | 571 BA, Berryhill - Sand Springs, Averitt |
| Miller | Concrete | 566 Woodward Park |

# If Something Looks Wrong

If a super's numbers are not showing: (1) confirm they selected the correct week in the Look-Ahead tool, (2) confirm they saw the green confirmation bar, (3) check the week picker in the Gantt matches the week they submitted. The most common issue is a week date mismatch.